## Timetable
Objectives | Tasks and steps | Outcome/Deliverable(s) | Lead | Completed/ Estimated duration
1. Communicate early successes stemming from FWS/USA-NPN partnership | Early successes stemming from the FWS/USA-NPN Partnership will be communicated to a broader audience, including details about implementation plans, project protocols, and data reporting through one-page handouts as well as online. Through these communications we will demonstrate how establishing phenology monitoring within a Refuge has led to enhanced baseline information, enhanced decision making, and/or improved communication with the public. | >> Julianna's report analyzing USFWS data in NPDb >> 1-pagers highlighting Refuges and how they are using Nature's Notebook | Erin | January 1, 2017 - 6/1/2017 One-pagers completed June 2017
2. Expand existing Refuge-based phenology trail projects and continue to seek other regional opportunities, ensuring data collection on target species occurs on and off Refuge | Each of the monitoring efforts on select cornerstone ecosystem species will be expanded geographically to increase the total number of observations available for use in research, land management, and decision making. We will build capacity for citizen scientist-based data collection through Americorps interns and other low-cost solutions for phenology monitoring program management. | Refuges are sucssessfully using Nature's Notebook to meet management and outreach objectives: >> Gulf Coast Phenology Trail >>Rio Grande Phenology Trail >>Mayfly Watch >>Other R3 Refuges (Minnesota Valley, Neal Smith, Sherburne) >>New Refuges (Midway Atoll) | Erin | ONGOING
3. Reboot of FWS subsite content and organization | We will reconsider the arrangement of content within the FWS subsite to improve access and accessibility. This will involve two major phases: a. Reorganize content – content will be reorganized with an eye toward engaging refuges and clearly communicating ways to get involved. b. Delivering refuge-specific information. Refuges collecting phenology data using Nature’s Notebook will each have a unique page, including information on the species being monitored, unit-specific activities, data display via phenology calendars and other maps or graphs, and unit-specific spring index information (drawing from #1 and #2, above). | >> Website with reorganized content >> Delivery of Refgue-specific information via unique webpages with species being monitored, unit-specific activities, data display via phenology calendars or other graphs, unit-specific spring index info | Erin | May 1, 2017 - 9/1/2017 Competed November 2017
4. Spring Indices within the Refuges | Following the model undertaken by B. Monahan et al. for NPS units, we will calculate the historical range of variability and trends in the onset of spring for each NWRS unit. This analysis will appear in a peer-reviewed publication. We will also provide custom interpretive information for each unit in the form of web-based and hard copy materials. | >> Report for Jana, Progress report, including maps of FLI and FBI over the last 10-30 years, based on Monahan | Theresa | 4/1/2017 initial analysis complete. Manuscript published Sept 2018 (https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0202495)
5. Ongoing communications with USFWS | · Periodic analysis of NPDb for Refuges monitoring phenology · Quarterly communication with participating Refuge staff I&M-VS · Document active Refuges on webportal | >> NWRS hierarchy in NPDb, communications with LPLs at Refuges >> Quarterly newsletter including: - Refuge highlights - Data analysis examples - New tools and technology - Example science/management questions - Data decision displays - Webinars and workshops hosted by NPN and NCTC >>Refuge bulletin pieces | Erin | ONGOING
6. Evaluation | - Develop a process for tracking the "early success" info sheets, their usage, and potential engagement of new refuges coming online. | Evaluation Report | LA/Erin | 2019-03-01

## Objective 1
Objective 1 Communicate early successes stemming from FWS/USA-NPN partnership Lead: Erin | Deliverable | Progress | Due | Complete
| >> Julianna's report analyzing USFWS data in NPDb >> 1-pagers highlighting Refuges and how they are using Nature's Notebook | 2/2/2017: Julianna has sent summaries of her analysis to Arctic NWR (Janet Jorgenson) and Don Edwards SF Bay NWR (Julie Kahrnoff) for their input on what they'd like to see in a one-pager | 2017-06-01 | Five one-pagers highlighting Refuges complete 8/3/2017
2/2/2017: Julianna is working on analysis for Valle de Oro NWR/Rio Grande Phenology Trail
2/16/2017: Julianna working on Valle de Oro analysis, moving onto Canaan Valley NWR analysis next
2/16/2017: Julianna is doing a poster on the FWS/NPN partnership, how Refuges are using NN for phenology monitoring needs, with a focus on 2-3 Refuges as case studies
4/27/2017: Julianna is wrapping up the Refuge case studies; will put these into a Report on the Data collected on the Refuges through Nature's Notebook
5/11/2017: Still waiting on feedback from Canaan Valley NWR and Valle de Oro NWR on their one-pagers; Waiting to hear back from Arctic NWR and Don Edwards NWR on photos to use in the templates; Erin will make sure all one-pagers have consistent formatting on the graphs and figures
6/8/2017: All Refuges have now given feedback on the figures to include; need to get feedback on one-pager draft from Canaan; all others have been given to Sara for formatting in the template
8/3/2017: Completed 5 Refuge Highlights, sent to Jana to distribute
9/28/2017: General FWS one-pager has been reviewed by Abe, Sara is putting it into template now for Jake to take to Reston next week
10/12/2017: Will plan to put the new NPN-FWS partnership one-pager on the About the Collaboration page on the new subsite
1/4/2018: Look into Refuge Bulletin; Open Spaces blog; I&M website
2/15/2018: Susan Morse, Communications Office with NWRS is working on an article about spring in the Refuges for the NWRS homepage
2/15/2018: Also sent info to Jana, but haven't heard if it went onto I&M website
3/29/2018: Susan Morse's NWRS article is out on the NWRS homepage: https://www.fws.gov/refuges/features/Timing-is-Everything.html
4/19/2018: UANews article out on lesser long nosed bat delisting and Flowers for Bats https://uanews.arizona.edu/story/uabased-network-looks-out-lesser-longnosed-bat
9/12/2018: Status of Spring in Refuges and Flyways paper media coverage: https://www.usanpn.org/SpringinRefugesandFlyways
9/17/2018: Worked with Lindsay Brady to submit piece on Status of Spring Tools to Fish and Wildlife News
11/6/2018: Submitted Research Note to Ecological Restoration, with Rob Taylor, Wieteke Holthuijzen, Ann Humphrey, Bridgette Flanders-Wanner on using phenology monitoring to aid invasive species eradication on Midway Atoll NWR
11/8/2018: Talked with Jason Goldberg and Mike Hudson from FWS Climate Adaptation Team about getting word out to FWS about phenology monitoring on Refuges, Status of Spring Tools

## Objective 2
Objective 2 Expand existing Refuge-based phenology trail projects and continue to seek other regional opportunities, ensuring data collection on target species occurs on and off Refuge Lead: Erin | Deliverable | Progress | Due | Complete
| >> Gulf Coast Phenology Trail >> Rio Grande Phenology Trail >> Mayfly Watch >> Other R3 Refuges >> New Refuges | 2/2/2017: Created landing page for Gulf Coast Phenology Trail (https://www.usanpn.org/fws/GulfCoastPhenologyTrail) | Ongoing
2/2/2017: Carly is working through LPL Certification Course, creating a Program Plan, and creating resources for volunteer trainings
2/2/2017: Tallie is getting some more schools into the Rio Grande Phenology Trail, monitoring similar plant species; she sent out a newsletter to the Trail contacts on Jan 27th
2/2/2017: Erin emailed Pam Steinhaus and Katie Julian to ask about their interest in Train-the-trainers workshop; Erin will follow up with other contacts from Melinda for R3 who might be interested; Jana is going to follow up with Mark's supervisor on whether we can get access to Mark's process, models
2/2/2017: Doing a Train-the-trainers workshop for Neal Smith NWR and Minnesota NWR March 7-8th
2/2/2017: Midway Atoll NWR is still collecting data
2/2/2017: Starting Nectar Connectors campaign this spring to collect data on monarch nectar plant phenology across the US
2/16/2017: Gulf Coast PT - adding new sites, getting ready for first volunteer training in mid-March
3/18/2017: Carrie held first GCPT training at Mississippi Sandhill Crane NWR; 10 participants from Master Naturalists, Master Watershed Stewards groups
4/25/2017: Tallie hosted screening of Crowd and the Cloud episode featuring Valle de Oro NWR at Bosque School
5/11/2017: Carly is still plugging away on working with people at different sites on the Gulf Coast, getting them up and running; Erin will reach out to Neal Smith folks to see if they are still planning on starting up their program in June
5/11/2017: Working on compiling resources for Flowers for Bats project. fws.usanpn.org/flowersforbats
6/8/2017: Meeting with Tucson Local Phenology Leaders next week to talk about plan for Flowers for Bats at botanical gardens, other places downtown
8/7/2017: Liz Gallagher started as Rio Grande PT Coordinator
9/14/2017: Gail Bishop hired as Gulf Coast PT Coordinator
9/28/17: Liz has set up a meeting with VdO staff to re-evaluate monitoring priorities, and perhaps add some new species from Nectar Connectors and SST; Liz doing VdO bday event this weekend; Gail and Erin will have regular check-ins every other week, Erin will ask Gail to organize check-ins with the other leaders on the Trail; Flowers for Bats - Sierra is working on reviewing historical datasets and finding out about other datasets for agaves and saguaros
10/12/2017: Liz is still working on integrating into Valle de Oro events, and representing the Trail; Gail is getting up and running with Trail activities, meeting with various Trail leaders, and planning out the upcoming workshop at Grand Bay; Neal Smith NWR had a workshop over the summer - need to ask them about how it went; Mayfly Watch - Mark Steingraeber got back in touch and wants to be involved going forward; Flowers for Bats - Sierra working through historical data, then will work on monitoring protocol; Erin will be giving workshop at NCTC next month for 15 or so participants; around 10 are FWS staff or volunteers; Also 4 Refuge people in the LPL Certification Course; we can try to target Urban Wildlife Refuges - ask Jana about what outlets they use to reach these folks, then ask Jennifer Owen-White/Liz to write up something about the benefits of NN from their perspective
11/3/2017: NCTC workshop - Planning a Phenology Monitoring Program on your Refgue - 5 Refuges represented, 3 other DOI partners
11/30/2017: Liz and Gail have finished the LPL Certification Course. Both still need to complete their program planning materials. Erin will follow up with them on these over the next couple weeks. Liz is planning an end of the year volunteer appreciation event; Saguaro NP seems interested in helping with Flowers for Bats
2/15/2018: Gail has trianing at Crosby Arboretum this Sat, working on getting more volunteers for different sites
2/15/2018: Looking into call for NWFW grants for monarch and pollinator conservation; focus on habitat improvement and outreach/coordination
3/15/18: Decided not to pursue NFWF grant due to limitations on funding match; potential new collaboration on Mayfly Watch with researchers at OU who study animal activty on weather radar; Flowers for Bats will have participation from multiple NPs and other organizations this year, as well as individual citizen scientists
5/1/2018: Conducted Flowers for Bats trainins at Tucson Botanical Gardens, Tohono Chul, Borderlands Restoration; 50 volunteers trained
6/7/18: GCPT first year annual report completed - https://fws.usanpn.org/sites/fws.usanpn.org/files/pdfs/GCPT_AnnualReport2017.pdf
6/26/2018: Met with Julie McIntyre (new Supervisory Biologist at Tucson office and SW Pollinator Coordinator for FWS) and Scott Richardson. Talked about Nectar Connectors (Julie will promote for us), other potential projects (Yellow-billed Cuckoo came up again) and Scott's interest in a further meeting with other FWS staff from Arizona and NPN to talk about other project ideas.
7/1/2018: Aaron Cajero, wildlife biologist at San Bernadino and Leslie Canyon NWR started agave monitoring for Flowers for Bats effort
7/3/2018: Started process to put Flowers for Bats monitoring protocol through FSP review - Brian Powell (Pima County) and Winifred Frick (Bat Cons Intl) will review
9/1/2018: Working with Jeff Fehmi, faculty at UA on project to monitor agave at SEAZ National Parks - his grad student doing weekly phenology monitoring for one year at all three parks, also monitoring soil moisture, other environmental variables
9/25/2018: Talked with Winifred Frick from Bat Conservation International about expanding Flowers for Bats effort to Baja California in Mexico. Will try to pilot effort next spring

## Objective 3
Objective 3 Reboot of FWS subsite content and organization Lead: Erin | Deliverable(s) | Progress | Due | Complete
| Updated website to improve access and usability a. Reorganize content – content will be reorganized with an eye toward engaging refuges and clearly communicating ways to get involved. b. Delivering refuge-specific information. Refuges collecting phenology data using Nature’s Notebook will each have a unique page, including information on the species being monitored, unit-specific activities, data display via phenology calendars and other maps or graphs, and unit-specific spring index information (drawing from Objectives #1 and #2). | Should start in April | 2017-09-01 | 2018-02-01
4/27/2017: Will meet with Lee/Jeff to talk about our thoughts for the reboot of the subsite; get their feedback on what is possible regarding dynamic visulizations on the Refuge landing pages
5/11/2017: Have started discussions with IT team about the changes to the subsite; Erin has reached out to Refuge staff to ask about what they would like to see on Refuge-specific webpages
6/8/2017: Still compiling feedback from various Refuge staff on visualizations they want to see on landing pages
7/13/2017: Erin has completed a first draft of a mock-up of the new subsite.
August: Terry Moody working on mock-ups of FWS subsite reboot
9/14/2017: IT team has started creating new FWS subsite based on mock-ups
9/28/17: Lee is working on translating Terry's designs to the web; DJ Case is working on filling in the requirements so they can give us a cost estimate
10/12/17: Lee is still working through Terry's designs, translating them onto the new subsite; DJ Case has started work on the Refuge Dashboard
11/302017: Subsite is almost ready to be rolled over to live
1/4/2018: Lee and Jeff and Erin meeting at 2pm to talk about the plans for Status of Spring - will likely roll out with recent status of spring, as we need to wait on the historical onset for the Si-x in the Refuges manuscript to be accepted
2/1/2018: rolled out Status of Spring page to new subsite (includes recent onset of spring info)
4/15/2018: Added Compliance info to FWS subsite, linked from footer: https://fws.usanpn.org/Compliance
6/1/18: Starting work on the second part of the Status of Spring page, the historical analysis that is in the Si-x in the Refuges manuscript
9/12/2018: New Long-term changes in the status of spring tool complete on website - fws.usanpn.org/status-spring
10/1/2018: Continued updates to Phenology on the Refuges landing pages and Refuge Dashboards, including addition of J.N. Ding Darling and Sevilleta NWRs
12/1/2018: Added additional landing pages for Gulf Coast Phenology Trail refuges, Patuxent Research Refuge

## Objective 4
Objective 4 Spring Indices within the Refuges Lead: Theresa | Deliverable(s) | Progress | Due | Complete
| Peer reviewed manuscript for the SIx on the Refuges | 2/2/2017: Jess Walker submitted a one-month progress report - https://docs.google.com/document/d/1tY55P1iW5IkKlfzB2AYB8Ndcuo_hiM96wC6kI42uE-s/edit?usp=sharing | Scoping and anayses due 4/1/2017 final project due May 2018 | 2018-09-12
2/16/2017: Check-in meeting with Jess and Jana on Feb 17th, to make sure we are on the right track toward meeting Jana's needs
3/7/17 - Eric shared an update; he and Jess have successfully replicated the Monahan et al work on refuges. Now we're grappling with how to expand on this in order to have enough novelty to the analyses and results to merit a peer-reviewed paper
3/15/17 – Jake passed $36K to USGS-Menlo Park to pay for Eric Waller to write up results (replicate Monahan et al. work), + add in something refuge-specific, and get submitted to a peer-reviewed journal like PLoS ONE
4/18/17 - Eric shared an update of his analysis where he evaluated changes in the timing of spring onset since ~1900 in each of the flyways. He had several questions about the best way to statistically handle the unbalanced design.
4/25/17 - Jake, Eric, and Jess Walker had a phone conversation to come up with ideas for how to best analyze the data on the flyways. Eric is currently processing more data, with focus on the latitudinal gradient. Also, Jake proposed to have a call w/this team + Jana to ensure that the direction Eric is going suits Jana's needs
5/11/2017: LA emailed Theresa to check about setting up a check in meeting with Eric, Jess, Jake, Jana, etc
6/8/2017: Eric, Jess, Theresa, Jake, Erin discussing figures to include in manuscript, how to highlight example bird species for analysis
7/13/2017: Paper team members have decided on figures for the paper. Eric working on first draft of text, will send to Erin and Theresa to add information
9/14/2017: Still working on draft of paper; Theresa and Eric are finalizing Methods and Results; will send to Jana in next couple weeks
9/28/2017: Send a draft of the paper to Jana, but she is OOO until October 15th. Plan is to try to submit to Plos One by end of October
11/30/2017: We have a complete draft of the paper; making final revisions; Jana is looking at it now; will have to go through FSP review
1/4/2018: Jess and Eric still have the manuscript, they are working on final updates to the figures; hopefully it will be submitted this month
1/17/2018: PLOS one paper submitted
4/12/2018: PLOS one paper accepted with minor revisions; working on revisions now to resubmit by May 18th
5/11/2018: Re-submitted PLOS paper
6/21/2018: Long-term status of spring tool is on the FWS development site; will be ready to launch after manuscript is published
9/12/2018: Manuscript published https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0202495; Status of Spring Tool updated on website fws.usanpn.org/status-spring

## Objective 5
Objective 5 Ongoing communication with Refuges Lead: Erin | Deliverable(s) | Progress | Due | Complete
| >> NWRS hierarchy in NPDb, communications with LPLs at Refuges >> Quarterly newsletter including: - Refuge highlights - Data analysis examples - New tools and technology - Example science/management questions - Data decision displays - Webinars and workshops hosted by NPN and NCTC >>Refuge bulletin pieces >> News blocks on webportal | 2/2/2017: Next newsletter to go out later in February, include information about Nectar Connectors Campaign | Ongoing
4/27/2017: Next newsletter to go our in May; include info on Refuge summaries that Julianna is working on, update to subsite
5/11/2017: Newsletter coming out this month, will highlight activities of Carly, Tallie, MN Valley, etc
6/8/2017: Sent Spring newsletter last week, highlighting Midway Atoll results and Flowers for Bats effort, Gridded phenology maps for Alaska
9/8/2017: Send summer newsletter, with 5 Refuge highlights; info about NCTC workshop
10/12/2017: Next up is fall newsletter, in November; will wait for the subsite to be released
1/4/2018: Next newsletter will go out in February; working to set up times to go over the Refuge Dashboards with small groups
2/8/2018: Sent FWS Quartlery newsletter announcing Status of Spring
6/18/2018: Sent FWS Quarterly newsletter with info on Dashboards, annual reports, etc.
9/14/2018: Sent FWS Quarterly newslettler with Long-term changes in the Status of Spring information
12/14/2018: Sent FWS Quarterly newsletter with summary of data collection in 2018

## Objective 6
Objective 6 Evaluation Lead: LA/Erin | Deliverable(s) | Progress | Due | Complete
| · Final Report on Phase III and Phase IV of this Partnership | Should start in November 2018 | 2019-01-31 | 2019-03-01
We can use our regular group survey process to get information from individual refuges and Phenology Trails at the end of 2017
9/28/2017: We may want to send a separate survey to our FWS partners. We can ask them specific quesitons, such as 'did you see the FWS Refuge Highlight sheets and did they help you design your program'
10/12/2017: Since the only FWS people who we talked to in the last year were in the LPL Certification Course, we can just send them the Course follow-up survey and not another survey; we need to try to figure out where the disconnect is between people collecting phenology data but not using NN; we can try to have meetings and focus groups to get these questions answered
12/10/17: Sent the Active Group Survey to all FWS leads.
5/1/2018: Shared back results of the Group Survey via FWS Newsletter: Our 2017 Local Phenology Project survey results shine light on how refuges are using phenology monitoring to meet their management and outreach objectives: The most common annual achievements described were (1) understanding the timing of important phenological events such as when to treat invasives, (2) training new observers, and (3) engaging the public in learning about refuge phenology The ways that refuges are informing their decisions with phenology data included (1) increasing the efficacy of control treatments of a high priority invasive species, (2) informing monitoring of flowering of focal species, (3) knowing when to clean out nest boxes for migrating birds The number of observers collecting data at individual refuges ranged from 1-50, with an average of 11-30 Over half of respondents engage student observers in K-12 or higher ed Over half of respondents have used the USA-NPN visualization tools
12/12/2018: Sent out Annual Group Survey for 2018
2/1/2019: Begn contacting refuge staff and volunteers to participate in focus group discussions and one-on-one conversations about their experience with phenology monitoring, what has and has not worked, etc.
3/20/2019: Began summarizing Annual Group Suvey responses from FWS staff, volunteers, and partners as well as feedback from focus group discussions and one-on-one conversations

## Reports
Report name | Weblink | Published/Released/Posted to Website Date
Phenology Report Guide | https://www.usanpn.org/files/npn/reports/USA-NPN-Phenology_Report_Guide.pdf | 2017-02-01
Phase I & II Program Evaluation and Final Report 2014-2017 | https://fws.usanpn.org/sites/fws.usanpn.org/files/pdfs/FWSUSA-NPNPartnershipPhaseIandIIEvaluationReport2017.pdf | 2017-04-01
USA-NPN 2017 Annual Report (highlight of Midway Atoll NWR) | https://www.usanpn.org/files/npn/reports/USA-NPN_annual_report-2017.pdf | 2017-04-01
USFWS and USA-NPN - helping the FWS Achieve its Mission Info Sheet | https://www.usanpn.org/files/npn/reports/USFWSandUSANPNPartnership2018.pdf | 2018-08-01
Diferential changes in the onset of spring across US National Wildlife Refuges and North American migratory bird flyways (PLOS One Manuscript) | https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0202495 | 2018-09-01
USA-NPN 2018 Annual Report (highlight of Si-x in the Refuges) | https://www.usanpn.org/files/npn/reports/USA-NPN-AnnualReport2018.pdf | 2019-03-01
Flowers for Bats monitoring protocol | https://fws.usanpn.org/sites/fws.usanpn.org/files/pdfs/NPNFlowersforBatsMonitoringProtocolFinal.pdf | 2019-03-01